## Slide 2
Applied Algorithm Lab
Make span schedule

## Slide 3: Make span schedule
Make a schedule for a project with many tasks.
A project has n tasks 1,..., n:
  Task i has duration d(i) to be completed
  Precedence constraints Q: for each (i,j) in Q, task j cannot be started before the completion of task i.
Objective: Arrange task the project to complete as soon as possible.
Input: n, |Q|, d(1),..., d(n), the set Q
Output: The earliest completion time of the project.

## Slide 4: Make span schedule
Example
Input | Output
8 9 15 30 80 45 4 15 15 19 1 2 2 4 3 4 4 5 2 6 3 6 5 7 6 7 5 8 | 148

## Slide 5: Make span schedule
Idea to solve: Formulate the problem using directed graph
  A graph with n nodes as n tasks
  If (i,j) Q, we draw an edge (i, j) on graph
    weight of edge (i,j) is t[i]
  The node having in-degree 0 : we can perform the corresponding task since t = 0

## Slide 6: Make span schedule
Idea to solve: BFS
  The node having in-degree 0 -> not affected by any other, but may affect some other nodes
  We use BFS to traverse, from a node y having in-degree 0
    Use auxiliary variable dist[x]: the first starting time of x
  After BFS all node: retrieve the node with maximal dist[]

## Slide 7
THANK YOU !